## Plan RET
MONTHLY MAINTENANCE PLAN OF THE TRANSMISSION LINES AND EQUIPMENTS
MONTH JUNE 2025 - VERSION 0
| Name of equipment | week
|  | 23 | 24 | 25 | 26/27
OHL 750 kV
LEA 400 kV
1 | Brazi Vest-Darste | 2-6.06
2 | Bucuresti Sud-Slatina |  |  | 16-20.06
3 | Bucuresti Sud-Cernavoda provizorat |  |  |  | 30.06-4.07
4 | Rosiori-Mukacevo | 2-13.06
5 | Racord U2 Cernavoda | 11.05-28.06
6 | Cernavoda-Constanta Nord | 2-13.06(no weekend)
7 | Rahman-Medgidia Sud |  |  | 16-20.06
8 | Isaccea-Stupina (provizorat) |  |  |  | 30.06-18.07(no weekend)
9 | Tantareni-Urechesti |  |  | 16-20.06
10 | Porti de Fier-Slatina |  | 10-16.06(no weekend)
11 | Urechesti-Rovinari G3+4 |  |  |  | 30.06-4.07
12 | Gutinas-Brasov |  |  |  | 23-25.06
13 | Isaccea-Smardan C1 | x | x | x | x
14 | Nadab-Bekescsaba |  |  |  | 23-27.06
OHL 220 kV
1 | FAI-Suceava | 2.06 |  | 18.06 | 30.06-4.07
2 | FAI-Gutinas | 5.06 |  | 19.06
3 | FAI-Munteni | 3.06 |  | 17.06
4 | Bucuresti Sud-Ghizdaru C1 der.Mostistea |  |  |  | 23.06-4.07
5 | Baia Mare3-Iernut |  |  | 16-20.06
6 | Cluj Floresti-Campia Turzii |  |  |  | 23.06-4.07(no weekend)
7 | Porti de Fier-Tr. Severin C2 |  |  | 17-23.06(no weekend)
8 | Porti de Fier-Tr. Severin C1 |  | 10-16.06(no weekend)
9 | Sardanesti-Urechesti | 2006-05-02
10 | Bradu-Stuparei | 2-6.06
11 | Targoviste-Ratesti |  |  | 16-20.06
12 | Bradu-Ratesti |  |  |  | 30.06-4.07
13 | Stuparei-Raureni |  |  |  | 23-27.06
14 | Lotru-Sibiu C2 |  |  |  | 30.06-4.07
15 | Baru Mare-Paroseni | 2-6.06
16 | Baru Mare-Hasdat |  |  | 16-20.06
17 | Mintia-Timisoara |  |  |  | 30.06-11.07
| OHL 110 KV interconnection |  | x
1 | Jimbolia-Kikinda
T +AT + BC + CS
1 | Suceava AT 200 MVA | 2.06
2 | FAI AT1 200 MVA | 4.06 |  | 16.06 | 23-27.06
3 | FAI AT2 200 MVA | 6.06 |  | 20.06 | 30.06-4.07
4 | Munteni AT 200 MVA |  | 10-13.06
5 | Gutinas AT5 400 MVA |  | 10-13.06
6 | Gutinas AT6 400 MVA |  |  |  | 30.06-4.07
7 | Ghizdaru AT2 200 MVA | 2-6.06
8 | Brazi Vest AT2 200 MVA |  |  | 16-20.06
9 | Mostistea AT 200 MVA |  |  |  | 23-27.06
10 | Targoviste AT1 200 MVA |  |  |  | 23-26.06
11 | Bucuresti Sud AT3 400 MVA |  |  |  | 30.06-4.07
12 | Gadalin BC 100 MVAr | 2-6.06
13 | Oradea Sud BC 100 MVAr |  | 10-13.06
14 | Rosiori BC 100 MVAr |  |  |  | 23-27.06
15 | Cernavoda BC1 100 MVAr |  |  | 16-27.06(no weekend)
16 | Tariverde Tr.1 250 MVA |  |  |  | 30.06-11.07
17 | Tulcea Vest Tr.1 250 MVA |  | 9-13.06
18 | Tulcea Vest Tr.2 250 MVA |  |  | 16-20.06
19 | Tulcea Vest Tr.3 250 MVA |  |  |  | 23-27.06
20 | Lacu Sarat AT3 400 MVA | 26.05-6.06
21 | Tantareni BCA 100 MVAr | 2-6.06
22 | Tr. Severin Est AT2 200 MVA |  |  | 17-23.06(no weekend)
23 | Tr. Severin Est AT1 200 MVA |  | 10-16.06(no weekend)
24 | Urechesti AT 200 MVA |  | 10-13.06
25 | Slatina AT2 200 MVA | 2-6.06
26 | Sibiu Sud Tr.3 250 MVA | 2-6.06
27 | Sibiu Sud Tr.4 250 MVA |  | 9-13.06
28 | Sibiu Sud AT5 400 MVA |  |  |  | 30.06-4.07
29 | Brasov Tr.1 250 MVA |  |  | 16-20.06
30 | Mintia AT2 200MVA | 26.05-6.06
31 | Arad Tr. 250 MVA |  | 10-20.06
32 | Timisoara AT2 200 MVA |  |  |  | 23.06-4.07
33 | Iaz AT2 200 MVA | 2-13.06
34 | Smardan Tr.1 250 MVA(actual Tr.3 250 MVA) | x | x | x | x
withdrawn in accordance with the yearly maintenance plan
withdrawn in period deferred over maintenance plan (full or partial)
withdrawn in addition with the yearly maintenance plan
permanent withdrawn from operation
x | it is not withdrawn, although it was in the yearly maintenance plan
withdrawn unavailable
T | transformer
AT | autotransformer
BC | shunt
CS | syncronous compensator