## Plan RET
MONTHLY MAINTENANCE PLAN OF THE TRANSMISSION LINES AND EQUIPMENTS
MONTH JULY 2025 - VERSION 0
Saptamana
| Denumire echipament | 27 | 28 | 29 | 30 | 31
OHL 750 kV
OHL 400 kV
1 | Bacau Sud-Roman Nord |  | 7-12.07
2 | Roman Nord-Suceava |  |  |  |  | 28.07-01.08
3 | Bucuresti Sud-Cernavoda provizorat | 30.06-4.07 | 7-11.07
4 | Brazi Vest-Domnesti |  |  |  |  | 28.07-01.08
5 | Cernavoda-Lacu Sarat derivatie Gura Ialomitei |  |  | 14-22.08
6 | Medgidia Sud-Dobrudja |  | 7-11.07 | 14-18.07
7 | Isaccea-Tulcea Vest |  |  |  | 21.07-01.08
8 | Isaccea-Stupina (provizorat) | 30.06-04.07 | 7-11.07 | 14-18.07
9 | Tantareni-Slatina |  |  | 14-18.07
10 | Urechesti-Domnesti |  |  |  | 23-25.07
11 | Urechesti-Rovinari G3+4 | 30.06-4.07 |  |  | 23-25.07
12 | Cernavoda-Pelicanu |  |  | x
13 | Isaccea-Vulcanesti |  |  |  | 21-31.07
14 | Arad-Sandorfalva |  |  |  |  | 28.07-01.08
15 | Isaccea-Smardan C1 | x | x | x | x | x
OHL 220 kV
1 | FAI-Suceava | 30.06-4.07 | 7-11.07
2 | FAI-Gutinas |  |  | 14-18.07 | 21-25.07
3 | Bucuresti Sud-Ghizdaru C1 der.Mostistea | 23.06-4.07
4 | Bucuresti Sud-Ghizdaru C2 |  | 7-11.07
5 | Brazi Vest-Teleajen |  | 7-11.07
6 | Cluj Floresti-Mariselu |  |  |  |  | 28.07-01.08
7 | Mariselu-CHE Mariselu TH2 |  |  |  |  | 28.07-01.08
8 | Mariselu-CHE Mariselu TH3 |  |  |  |  | 28.07-01.08
9 | Cluj Floresti-Tihau |  |  |  | 21-25.07
10 | Cluj Floresti-Campia Turzii | 23.06-4.07(no weekend)
11 | Bradu-Ratesti | 30.06-4.07
12 | Isalnita-Gradiste |  |  |  | 21-28.07
13 | Porti de Fier - TH3 | 1-4.07
14 | Porti de Fier - TH1 |  | 7-10.07
15 | Paroseni-Tg.Jiu Nord |  |  |  |  | 28.07-01.08
16 | Urechesti-Tg.Jiu Nord |  |  |  |  | 30-31.07
17 | Arefu-Raureni |  | 7-11.07
18 | Lotru-Sibiu C2 | 30.06-4.07
19 | Lotru-Sibiu C1 |  | 7-11.07
20 | Fantanele-Gheorgheni |  | 7-11.07
21 | Resita-Iaz C2 | 30.06-11.07
22 | Mintia-Timisoara | 30.06-11.07
23 | Resita-Timisoara C1 |  |  | 14-25.07
OHL 110 KV interconnection
T +AT + BC + CS
1 | FAI AT2 200 MVA | 30.06-4.07 | 7-11.07
2 | Gutinas AT6 400 MVA | 30.06-4.07
3 | Suceava AT 200 MVA |  | 7-11.07
4 | Bacau Sud Tr. 250 MVA |  |  | 14-17.07
5 | Roman Nord Tr. 250 MVA |  |  |  | 21-27.06
6 | Gura Ialomitei Tr.4 250 MVA |  | 7-11.07
7 | Bucuresti Sud AT3 400 MVA | 30.06-4.07
8 | Brazi Vest AT3 400 MVA |  |  | 14-18.07
9 | Targoviste AT2 200 MVA |  |  |  |  | 28.07-01.08
10 | Rosiori AT2 400 MVA |  |  | 14-18.07
11 | Oradea Sud BC 100 MVAr | 30.06-20.07
12 | Tariverde Tr.1 250 MVA | 30.06-11.07
13 | Tariverde Tr.2 250 MVA |  |  | 14-25.07
14 | Tariverde Tr.3 250 MVA |  |  |  |  | 28.07-01.08
15 | Barbosi AT1 200 MVA |  | 7-11.07
16 | Cetate AT 200 MVA |  | 7-11.07
17 | Urechesti AT 400 MVA |  |  |  | 21-22.07
18 | Arefu AT1 200 MVA |  |  |  | 21-25.07
19 | Arefu AT2 200 MVA |  |  | 14-18.07
20 | Sibiu Sud AT5 400 MVA | 30.06-4.07
21 | Sibiu Sud AT6 400 MVA |  | 7-11.07
22 | Brasov Tr.2 250 MVA |  |  | 14-18.07 | 21-25.07
23 | Darste Tr.2 250 MVA |  |  |  |  | 28.07-08.08(no weekend)
24 | Iaz AT1 |  |  | 14-25.07
25 | Timisoara AT2 200 MVA | 23.06-4.07
26 | Mintia AT3 400 MVA |  |  |  |  | x
27 | Smardan Tr.2 250 MVA | 01-31.07
withdrawn in accordance with the yearly maintenance plan
withdrawn in period deferred over maintenance plan (full or partial)
withdrawn in addition with the yearly maintenance plan
permanent withdrawn from operation
x | it is not withdrawn, although it was in the yearly maintenance plan
withdrawn unavailable
T | transformer
AT | autotransformer
BC | shunt
CS | syncronous compensator