## Plan RET
MONTHLY MAINTENANCE PLAN OF THE TRANSMISSION LINES AND EQUIPMENTS
MONTH NOVEMBER 2025 - VERSION 0
| Name of equipment | week
|  | 44 | 45 | 46 | 47 | 48
OHL 750 kV
OHL 400 kV
1 | Bacau Sud-Roman Nord |  | 03-04.11
2 | Medgidia Sud-Dobrudja | 27.10-07.11
3 | Lacu Sarat-Smardan |  |  | 10-14.11
4 | Isaccea-Lacu Sarat |  |  |  | 17-21.11
5 | Isaccea-Stupina provizorat |  | 03-06.11
6 | Isaccea-Vulcanesti |  | 8-11.11
7 | Mintia Sibiu Sud |  | 03-07.11
8 | Iernut-Sibiu Sud |  |  | 10-14.11 | 17-21.11
9 | Darste-Brasov |  |  |  |  | 24-28.11
10 | Mintia-Arad | 13.10-02.11
11 | Resita-Pancevo C1 |  |  | 10-14.11
12 | Resita-Pancevo C1 |  |  | 10-14.11
OHL 220 kV
1 | FAI-Suceava |  |  | 10-14.11 | 17-21.11
2 | Dumbrava-Stejaru | 05-07.11
3 | Lacu Sarat-Filesti |  |  |  |  | 24-28.11
4 | Baru Mare-Hasdat |  |  |  |  | 24-28.11
5 | Craiova Nord-Isalnita C1 | x
OHL 110 KV interconnection
T +AT + BC + CS
1 | Rosiori AT2 400 MVA |  | 03-09.11
2 | Tantareni BCB | x(a day)
3 | Smardan Tr.2 nou 250 MVA
withdrawn in accordance with the yearly maintenance plan
withdrawn in period deferred over maintenance plan (full or partial)
withdrawn in addition with the yearly maintenance plan
permanent withdrawn from operation
x | it is not withdrawn, although it was in the yearly maintenance plan
withdrawn unavailable
T | transformer
AT | autotransformer
BC | shunt
CS | syncronous compensator